## Slide 1: Global Safety Reporting Harmonization Working Group Planning 2019 Jan 8, 2019

## Slide 2: Agenda
Objective:
  Align on the objectives and scope of putting in place an industry working group to develop and maintain the Safety Reference Model
Topics:
  Why are we doing it and what are the benefits?
  Define what the SRM is
    Scope/deliverables
    Who owns it ?
      WCG or the working group
  How will membership be defined
    Current clients vs intended clients vs all welcome?
    Internal resources and staff
  Confirm timelines
  Communications
    Internal
    External
  Next steps
Notes: Why are we doing it and what are the benefits?
For the global good and drive global harmonization
  Someone has to go first so lets build on what we have started
Internally
  Maintains our Core product
  Adds value to core product
  Protects against competitors
Do this activity under sales and marketing budget/cost centre

## Slide 3: Problem Statement
There is no commonly accepted standard interpretation for distributing safety reports globally to clinical trial sites and ethics committees
Every country uniquely regulates when and how investigators, ethics committees, and health authorities receives new safety reports on investigational medicinal products (IMP) throughout the development cycle of human research. Regulations are often vague and open to interpretation.
Biopharma & CROs uniquely interpret local country rules on what safety information should be distributed to participating parties in a given country. Many companies distribute all safety reports to ensure they don’t accidentally hold back distribution due to lack of clarity in regulations.
Sites are overwhelmed with over-reported and cross-reported safety reports due to common practices such as “brute-force” distribution to all potential recipients and over-distribution.

## Slide 4: Mission Statement
Global Safety Reporting Harmonization Working Group:
Our mission is to create and drive adoption of best practices in safety reporting that will improve how Sponsors and CROs share safety information with clinical trial sites/ethics thus eliminating over distribution and improving safety communication with sites and ethics so that they have the information they need to effectively and efficiently manage patients in the study.
  Drive global harmonization in reporting rules for Investigators and IRB/IECs by creating a reference model of global safety reporting rules
  Develop models for “niche” countries where regulations are unknown so as not to delay site/study activation
  Understand the process flows from handoff from the Sponsor to the clinical trial site
Notes: First Point: adopt these rules among our representative companies, and make them available for the industry to enable precision distribution of safety reporting in accordance with global regulatory requirements.

## Slide 5: What will the output look like of the working group*?
Safety Reference Model - Document Characteristics
  SUSARs
    7/15 Day
    Causality expectations
    Unanticipated events
  “Other” events/unanticipated problems qualify expedited reporting
  Aggregate reports
  Reference Safety/Product Information
2. Safety Reference Model – Country Characteristics
  Blinded/Unblinded distribution requirements
  Tier 1 and Niche Country models
3. Oversight and updates procedures
  Global Safety Reporting Glossary
  Periodic Review
  “Factory Setting” changes
  Communication
*The Safety Reference Model will use globally recognized terminology used in safety reporting
Notes:     Address global harmonization
    Data driven decisions around country rules when regs are grey

## Slide 6: How will the Working Group get started?
WCG will host two working group sessions in the first half of 2019 with representatives from leading biopharma, large CROs, site representation, regulators, and large ethics committees.
  Invitations to potential targeted participants will be sent by mid-November to establish intent to participate, share a target date and location for the first meeting, and to share the mission
WCG will provide the initial draft safety reference model currently adopted by multiple large pharma/CROs
  Initial Draft Global Safety Reference Model Completed
The first working group is targeted to take place Q1 2019 and will agree upon the framework for rules, the form of the draft, and how each representative company will buy-in or propose changes to the reference model
A second working group is planned to take place Q2 2019 to review member feedback and finalize the first Global Safety Reference Model
  Final version will be made available for Working Group members.
  Members can share within their representative organizations and assess implementation and adopting as part of there standard processes

## Slide 7: How will this happen?
WCG will host two working group sessions in the first half of 2019 with representatives from leading biopharma, large CROs, site representation, regulators, and large ethics committees.
WCG will provide an initial draft reference model of precision rules adopted by multiple large pharma/CROs where human research is conducted
The first working group will be held by February 2019 and will agree upon the framework for rules, the form of the draft, and how each representative company will buy-in or propose changes to the reference model
A second working group will be held by May 2019 with compiled feedback and will finalize the initial reference model for broad release
  Representative companies will then begin ensuring adoption within their businesses of these rules
WCG will make available and release the a Global Safety Rules Reference Model 1.0 by June 15, 2019
Outdated

## Slide 8: SRM Landscape –Phased Approach to Global Harmonization
Phase 1 - Get it started for Sponsored Interventional (IMP) studies
  Sites and ethics
  Updates
Phase 2 – Include expanded study types
  Investigator Initiated
  Post marketing (NIMP)
  Umbrella studies
Phase 3 - Focus on “Housekeeping”
  Stopping Rules
  RSI
  Translations
  Other
  Study design/Institution influences
Phase 4 - Medical devices
  Develop Strategy for managing medical device studies
  Combination studies
Phase 5 - IRB/IEC needs (and EU Portal)
  Local vs country needs
Phase 6 - Consider Health Authorities

## Slide 9: Targeted Participants –See SRM working group.xls
Membership Profile
Influencers within there organization
  Decision Makers
  Ability to implement change
Areas of expertise
  Quality
  Clinical Operations
  Regulatory
  Drug Safety
  Global Vision
Available to contribute
  How much time is expected
    Define what we want them to do
      develop vs confirm
Question: Do they need to be SafetyPortal/WCG Clients?
  Deliverables would be shared with working group members

## Slide 10: Planning
Activity |  |  | 
Confirmed scope |  |  | 
CAR and Change Summary |  |  | 
CAR Oversight SOP |  |  | 
Confirmed Invitees |  |  | 
Information Package |  |  | 
Kick off meeting |  |  | 
F2F Planning | ????? Doubt we can do |  | 
Project planning and budget |  |  | 

## Slide 11: Back Up and Supplemental Slides

## Slide 12: What will the output look like of the working group?
3
SUSAR
Yes/No
Aggregate reporting
Non Sponsor Comparator
Other Safety Communications/Updates
Reference safety Information
IB and updates
Domestic
Protocol
Domestic+ Protocol
7 Day alert
Yes/No
*Depending on Sponsor policy, frequency and availability of reports can vary
*Drug Safety typically accountable for defining if an event meets the definition of a SUSAR
Yes/no
If Yes:
Causality
Dear Investigator Letters/Unanticipated problems
Urgent Safety Communications
* Typically all active sites should receive safety communications necessitating a change to the risk benefit profile warranting a change in IC or protocol
Yes/No
If Yes:
Causality
Domestic
Protocol
Domestic+ Protocol
7 Day alert
* Sponsor policy should determine distribution as per the IB effective date vs version date
DSUR
Required by ethics in some countries
Local/Regional labels if approved
Document Characteristics
Responsible for Notifying IRB/IEC
Sponsor/Investigator
Unbinding Requirements
* Central ethics typically managed by Sponsor
Translations
Rules defined for Clinical programs or medical devices
Investigator and study staff should remain “blinded” to preserve the integrity of the blind of the study
Local Language required
Accept initial report to comply with reporting timelines
Additional rules for early Phase
Yes/no
Yes/No
Prepare for next phase of SRM
*If Investigator, will need to receive on IRB/IEC behalf
Country Characteristics
We will produce a reference model of interpreted regulations on:

## Slide 13: WCG Expanding Partnership with Clients
We believe that a successful partnership includes the following components:
Governance at all levels
Executive Sponsorship
Clear goals and expectations
Transparency
Sense of urgency
Communication at all levels
Shared risk shared success
Accountability and Responsibility
1. Accelerate the Value
3. Share the Success
2. Utilize our Experts